## Sheet1
Sr.No. | Task Description | Action_Owner | ETA | Status | Remarks
1 | Build the Logic for HUL110 OLT Data FDT splicing details and generate the complete file data output for HUL110 | Karan / Adithya/ Wilbur | 2025-11-05 | WIP
2 | FDT complete Data Extraction using tool and compare with Complete HUL110 Data | Adithya / Karan | 2025-11-05 | Done
3 | FAT to FAT Complete data extration | Gaurav / Karan / Srishti | 2025-11-06 | Done
4 | FAT to FAT tool extracted data compare with HUL110 Compete data | Gaurav / Karan | 2025-11-07 | Done
5 | Data Extraction Tool deployment on AWS EC2 machine | Vishal | 2025-11-04 | Done
6 | FAT to FAT data modification on tool option is required - development | Vishal / Gaurav | 2025-11-10 | WIP
7 | extracted Data load in NetBox to Fiber Network View | Jayaram / Nayan
8 | PDF to Jason FAT & Excel to FAT data comparion output | Adithya/Gaurav/ Vishal | 17-11-2025 19/11/2025 |  | To be reviewed first 5 files share the descripency list
9 | HUL103 FAT data validation ( Updated logic for the Splice Enclosue to be updated) | Gaurav / Karan / Srishti | 2025-11-18 |  | Update the logic and share the data for HUL103
10 | FAT splitter mismatch between PDF & Excle Splice Matrix(HUL103, 104, 107, 112, 115) | Adithiya/ Srishti | 2025-11-17 |  | Check and and create the exception report against the OLT's
11 | Excel/ CSV data merge into single file | Srishti / Karan | 2025-11-17 | Done
12 | Data extract from Tool with FDT Name | Vishal | 2025-11-14 | Done
13 | FAT Data integration into Tool & Extract the complete data. | Vishal | 2025-11-17
14